CODEVELIX

Website & Software Development Company

codevelix.com  |  info@codevelix.com  |  +92 306 4228502

Lahore, Pakistan

TECHNICAL & FINANCIAL QUOTATION

Odoo ERP Implementation — Apparel Manufacturing & Retail

| Quotation No. | CVX-Q-2026-0822-001 |
| --- | --- |
| Date | 22 August 2026 |
| Valid Until | 30 days from date of issue |
| Prepared For | Zeenat Pret (SMC) Pvt Ltd |
| Client Address | Building No 4, St No 1, Muhammad Ali Chowk, Lahore, Pakistan |
| Industry | Apparel Manufacturing & Retail (Zeenat Pret & Gulposh brands) |
| Prepared By | Codevelix — ERP & Custom Software Division |
| Reference Documents | Scope of Work (Odoo ERP) v1.0 + Zeenat Pret Software Requirements Specification v1.0 |
| Solution | Odoo Enterprise v19 (recommended) with apparel-specific customizations |

CONFIDENTIAL — Prepared solely for Zeenat Pret (SMC) Pvt Ltd

# 1. Executive Summary

Codevelix proposes a full Odoo Enterprise ERP implementation for Zeenat Pret (SMC) Pvt Ltd, covering apparel manufacturing, finished-goods packing store, outlet retail (POS), accounts, HR/payroll, purchase, inventory, gatepass/dispatch, and third-party integrations.

This quotation is prepared based on:

Scope of Work (Odoo ERP) — Zeenat Pret document (Enterprise v19, 15 module areas)

Zeenat Pret Software Requirements Specification — detailed operational workflows (Job Card, embroidery, backup store, weekly worker payments, Vyapar-style accounts, gatepass, FG store scan/dispatch, outlet POS)

Our approach combines standard Odoo Enterprise capabilities with targeted custom development for apparel-specific production, worker piece-rate payments, barcode/variant stock control, and department-connected accounting — aligned with your golden rule: ONE TRANSACTION = ONE ENTRY.

## 2. About Codevelix

Codevelix is a Lahore-based website and software development company specializing in custom web applications, ERP, CRM, POS, and SaaS solutions. We deliver end-to-end: discovery, design, development, QA, deployment, training, and post-launch support.

| Contact | Detail |
| --- | --- |
| Website | https://codevelix.com |
| Email | info@codevelix.com |
| Phone / WhatsApp | +92 306 4228502 |
| Location | Lahore, Pakistan |
| Core Services | ERP, Web Applications, POS, Mobile Apps, Website Development, Maintenance |

# 3. Project Overview

| Item | Detail |
| --- | --- |
| Client | Zeenat Pret (SMC) Pvt Ltd |
| Brands | Zeenat Pret & Gulposh (single legal entity, brand-wise segregation) |
| Business Type | Apparel manufacturing, packing store, outlet retail, online (Shopify) |
| Proposed Platform | Odoo Enterprise Version 19 |
| Deployment | Odoo.sh Cloud (recommended) or client-hosted — to be confirmed |
| Licensed Users | To be confirmed by Client (not included in implementation fee) |
| Engagement | Full ERP implementation with apparel customizations |
| Estimated Duration | 5–7 months (subject to client sign-offs and data readiness) |
| Primary Location | Lahore, Pakistan — onsite RG, training; offsite development |

## 3.1 Proposed Delivery Phases

| Phase | Activity | Location | Duration (Est.) | Key Output |
| --- | --- | --- | --- | --- |
| 1 | Requirement Gathering & System Study | Onsite — Lahore | 3–4 weeks | Signed Business Requirement Document (BRD) |
| 2 | Core Configuration & Standard Modules | Offsite | 4–6 weeks | Configured Odoo instance (CRM, Sales, Purchase base, Inventory base) |
| 3 | Custom Development — Production & Manufacturing | Offsite | 8–10 weeks | Job Card, embroidery, backup store, operations, wages |
| 4 | Custom Development — Accounts, FG Store, Gatepass, POS | Offsite | 6–8 weeks | Worker payments, scan dispatch, gatepass, outlet POS customizations |
| 5 | HR, Payroll & Integrations | Offsite | 4–5 weeks | HR/payroll (PF/EOBI), Shopify, courier, FBR, biometric |
| 6 | Data Migration, UAT & Training | Onsite + Offsite | 3–4 weeks | Master data loaded, users trained, UAT sign-off |
| 7 | Go-Live & Hypercare | Onsite + Offsite | 2 weeks + 3 months | Production live, post-go-live support |

# 4. Scope of Work Summary

The following scope aligns the Odoo SOW module list with Zeenat Pret's detailed operational requirements.

| # | Module / Area | SOW Reference | Zeenat Pret Requirements | Delivery Type |
| --- | --- | --- | --- | --- |
| 1 | User Management & Access Control | SOW §4.1 | Role-based access all departments | Default Odoo + Config |
| 2 | Approvals | SOW §4.2 | Purchase, stock requisition, general approvals | Default Odoo + Config |
| 3 | CRM | SOW §4.3 | Pipeline, leads, customer management | Default Odoo + Config |
| 4 | Sales | SOW §4.4 | SQ/SO, pricelist, PDF templates | Default + Custom PDF |
| 5 | Outlet POS | SOW §4.4.1 | Barcode sale, returns, cash closing, day book | Default + Custom |
| 6 | Purchase / Procurement | SOW §4.5 + Req §4 | Fabric, accessories, GRN/QC, issue, return, low stock | Default + Custom |
| 7 | Inventory & Warehouse | SOW §4.6 + Req §5 | Article+Color+Size+SKU, variant stock, locations | Default + Custom |
| 8 | Quality Management | SOW §4.7 | QC at receipt, production, transfer | Default + Config |
| 9 | Manufacturing / Production ★ | SOW §4.8 + Req §6 | Job Card, embroidery, backup store, wages, costing | Heavy Custom |
| 10 | Maintenance | SOW §4.9 | Equipment & preventive maintenance | Default Odoo |
| 11 | Invoicing | SOW §4.10 | Customer/vendor invoices, payments | Default + Custom PDF |
| 12 | Accounting & Finance ★ | SOW §4.11 + Req §7 | Ledgers, worker weekly pay, petty cash, reconciliation, P&L | Default + Heavy Custom |
| 13 | HR ★ | SOW §4.12 + Req §3 | Enrollment, attendance, shifts, leaves, advances, performance | Default + Custom |
| 14 | Payroll ★ | SOW §4.13 + Req §3 | Salary, PF, EOBI, income tax, payslips | Default + Custom (Pakistan) |
| 15 | FG Packing Store & Gatepass ★ | Req §7, §8 | Scan receive, dispatch, Shopify, gatepass reports | Custom Module |
| 16 | Productivity & Communication | SOW §4.14 | Documents, calendar, discuss, dashboards | Default Odoo |
| 17 | Integrations | SOW §4.15 + Req §9 | Shopify, courier, FBR, biometric, email, barcode | Custom Integration |

★ = Modules with significant custom development based on Zeenat Pret apparel workflows.

# 5. Key Custom Development Scope (Zeenat Pret Specific)

Based on your Software Requirements Specification and production workflow documents:

## 5.1 Production — Job Card & Manufacturing Workflow

Job Card master control (Article, Tech Pack, BOM, planned qty, color, embroidery instructions)

Embroidery repeat planning with configurable machine-head standards (24-head / 28-head meters per repeat)

Backup Store register — reserve non-embroidered components against Job Card; release after embroidery reconcile

Stage-wise issue/receive reconciliation (Dyeing, Embroidery, Cutting, Stitching, Press, Packing, FG)

Size-wise production control (Planned vs Cut vs Stitched vs Packed Good vs Short)

Daily worker operation entry → auto payable (piece-rate for stitchers, press, packing teams)

Pre-cost vs post-cost per article/collection with variance reporting

Live WIP dashboard: current stage, location, ageing, bottlenecks, management alerts

## 5.2 Accounts — Connected & Audit-Friendly

ONE TRANSACTION = ONE ENTRY — auto posting from Production, Store, Outlet, Purchase

Weekly worker/job-work payment settlement (stitchers, press, packing) with article-wise audit detail

Worker ledger: opening, this week work, advance/deduction, net, paid, closing

Petty cash, cash & bank, automatic day book

Department reconciliation (Production, FG Store, Outlet, Shopify, Courier COD, Purchase)

Vyapar-style vouchers, party ledgers, period lock, full audit trail

## 5.3 Finished Goods / Packing Store & Gatepass

Production-to-store receiving with barcode/SKU scan (Article + Color + Size)

Dispatch types: Outlet transfer, Direct customer, Shopify order, Courier

Scan controls: wrong item block, duplicate block, qty complete confirmation

Gatepass generation for pack/dispatch with daily, weekly, monthly, annual reports

Stock dashboard: in hand, reserved, in transit, dispatched, returns/RTO, low stock

## 5.4 Outlet POS

Barcode/SKU sale flow with hold/resume, return/exchange from original invoice

Split payments (Cash/Card/Bank/Online/Cheque), partial/credit sales

Outlet stock transfer (Draft → Dispatched → Received), adjustment, audit

Daily outlet closing: opening cash + received − paid = expected closing

Auto Day Book and accounts posting — no duplicate entry

## 5.5 HR & Payroll

Employee enrollment, shifts, daily attendance (manual + biometric integration)

Attendance correction with audit; annual leaves with accrual and approval

Advance salary request, approval, recovery in payroll

PF, EOBI, income tax withholding (Pakistan statutory)

Increments, allowances, performance history on employee profile

## 5.6 Purchase & Material Store

Fabric and accessories purchasing with PO → GRN → QC → stock

Issuance to Job Card/department; rejection, return, exchange

Low stock alerts (daily/monthly reports)

## 5.7 Integrations

Shopify — orders, inventory reserve/fulfill, tracking sync

Courier company — shipment tracking, COD settlement

FBR e-invoicing — sales tax compliance

Biometric attendance devices

Email server for system communications

# 6. Financial Proposal

All amounts in Pakistani Rupees (PKR). Odoo Enterprise license fees, hosting (Odoo.sh), and third-party app costs are excluded unless stated otherwise.

## 6.1 Implementation Services — Fixed Price Estimate

| Ref | Work Package | Description | Amount (PKR) |
| --- | --- | --- | --- |
| A | Project Management, Kick-off & Requirement Gathering (Phase 1) | Onsite BRD, process mapping, gap analysis | 425,000 |
| B | Core Odoo Setup — Users, Approvals, CRM, Sales, Base Config | Company/brand setup, roles, approval matrix | 380,000 |
| C | Purchase, Inventory & Quality Management | Fabric/accessories, GRN/QC, variants, barcode, low stock | 520,000 |
| D | Manufacturing / Production ★ (Custom) | Job Card, embroidery, backup store, stages, wages, costing, WIP dashboard | 1,950,000 |
| E | Accounting & Finance ★ (Custom) | Worker weekly payments, petty cash, day book, reconciliation, P&L | 820,000 |
| F | Finished Goods Store, Gatepass & Dispatch ★ (Custom) | Scan receive/dispatch, gatepass, period reports | 680,000 |
| G | Outlet POS ★ (Custom) | Retail POS, returns, cash closing, stock transfer | 480,000 |
| H | HR & Payroll ★ (Custom) | Attendance, leaves, advances, PF/EOBI/tax, payslips | 580,000 |
| I | Integrations | Shopify, courier, FBR, biometric, email | 620,000 |
| J | Invoicing, Maintenance, Productivity Modules | Standard configuration | 180,000 |
| K | QA, UAT Support & End-User Training | Onsite training per module, UAT coordination | 380,000 |
| L | Data Migration & Go-Live | Master data templates, opening balances, production cutover | 320,000 |
| M | Post Go-Live Hypercare (3 months) | Bug fixes, priority support, minor adjustments | 270,000 |

Subtotal (Implementation Services): PKR 7,605,000

## 6.2 Optional / Client-Direct Costs (Not Included Above)

| Item | Estimated Range (PKR) | Notes |
| --- | --- | --- |
| Odoo Enterprise User Licenses | As per Odoo pricing × user count | Client procures directly or via Codevelix as reseller if available |
| Odoo.sh Hosting (annual) | Approx. USD 500–2,000+/year | Depends on plan and users; client account recommended |
| Third-Party Odoo Apps (if required) | Variable | Confirmed post Requirement Gathering |
| Biometric Hardware / Scanners | Client hardware cost | Codevelix integrates; devices supplied by client |
| Historical Data Migration | 450,000+ (if required later) | Not in base scope — opening balances only included |
| Additional Brands / Legal Entities | Change Request pricing | Base quote covers 1 entity, 2 brands |
| Onsite Support Beyond Quoted Days | PKR 25,000 / day | Travel within Lahore; outstation at actual cost |

## 6.3 Total Investment Summary

| Description | Amount (PKR) |
| --- | --- |
| Implementation Services (Items A–M) | 7,605,000 |
| Professional Services Tax (if applicable) | As per prevailing FBR rules |
| Grand Total — Implementation (excl. licenses & hosting) | 7,605,000 |

Final fixed price will be confirmed in a formal Statement of Work (SOW) after Requirement Gathering sign-off. Items marked ★ may be adjusted ±10% based on validated BRD scope.

# 7. Payment Terms

| Milestone | % | Amount (PKR) | Trigger |
| --- | --- | --- | --- |
| Advance on Contract Signing | 25% | 1,901,250 | Signed quotation + project kick-off |
| Phase 1 Complete — BRD Sign-off | 15% | 1,140,750 | Approved Business Requirement Document |
| Phase 3 Complete — Production Module UAT Ready | 20% | 1,521,000 | Production custom modules demo approved |
| Phase 4–5 Complete — Accounts, FG, POS, Integrations UAT Ready | 20% | 1,521,000 | Remaining custom modules demo approved |
| Go-Live Sign-off | 15% | 1,140,750 | Production environment live + client acceptance |
| Hypercare Completion (3 months post Go-Live) | 5% | 380,250 | End of hypercare period |

## 8. Deliverables

| Phase | Deliverable |
| --- | --- |
| 1 | Business Requirement Document (BRD) — client sign-off required |
| 2 | Configured & customised Odoo Enterprise instance (staging + production) |
| 3 | Custom modules: Production Job Card, Accounts worker payments, FG Store, Gatepass, POS enhancements |
| 4 | Integration connectors (Shopify, courier, FBR, biometric — as scoped) |
| 5 | Data migration templates + one full import cycle (master data + opening balances) |
| 6 | End-user training sessions (onsite — Lahore) + admin training |
| 7 | UAT test scripts + hypercare support for 3 months post go-live |
| 8 | Technical documentation + user guides (module-wise) |

## 9. Timeline Estimate

Estimated total project duration: 5–7 months from contract signing, subject to:

Timely client sign-offs on BRD, UAT, and go-live approval

Client provides master data, opening balances, PDF templates, and API credentials on schedule

Key resources available for onsite Requirement Gathering and training in Lahore

No major scope changes after BRD sign-off without Change Request

## 10. Exclusions

Odoo Enterprise license subscription fees

Cloud hosting (Odoo.sh) subscription

Historical transactional data migration (prior years)

Hardware (servers, biometric devices, barcode scanners, POS terminals)

Internet connectivity, domain, SSL at client premises

Ongoing ERP support beyond 3-month hypercare (available as separate AMC)

Upgrade to future Odoo major versions

Legal/tax advisory beyond system configuration for Pakistani tax localisation

## 11. Assumptions

Single legal entity with two brands (Zeenat Pret & Gulposh) in one Odoo database

Client confirms licensed user count before environment setup

Client provides approval matrices, PDF template designs, Chart of Accounts, and process details before respective configuration

Client executes UAT and provides sign-off within agreed testing window

One full data import cycle included; re-imports due to client data errors subject to Change Request

Third-party integrations contingent on client providing API credentials before development

Final scope per Odoo SOW v1.0 and Zeenat Pret Software Requirements Specification v1.0, refined at BRD

## 12. Change Request Policy

Any requirement not explicitly covered in the signed BRD will be handled via written Change Request (CR) with impact assessment on cost and timeline before work commences. Codevelix hourly rate for CR work: PKR 8,500/hour (or PKR 25,000/day onsite).

## 13. Annual Maintenance (Optional — Post Hypercare)

| Plan | Coverage | Annual Fee (PKR) |
| --- | --- | --- |
| Basic AMC | Bug fixes, minor config, backup monitoring, 8 hrs/month support | 360,000 |
| Standard AMC | Basic + small enhancements, priority support, 16 hrs/month | 720,000 |
| Premium AMC | Standard + dedicated support window, 32 hrs/month, quarterly review | 1,200,000 |

AMC pricing effective after hypercare period; optional and quoted separately.

# 14. Quotation Acceptance

By signing below, the authorised representative of Zeenat Pret (SMC) Pvt Ltd accepts this quotation and authorises Codevelix to proceed with Phase 1 (Requirement Gathering) upon receipt of the advance payment.

|  | Codevelix | Zeenat Pret (SMC) Pvt Ltd |
| --- | --- | --- |
| Authorised Name |  |  |
| Designation |  |  |
| Signature |  |  |
| Date |  |  |
| Company Stamp |  |  |

— End of Quotation —

Quotation Ref: CVX-Q-2026-0822-001  |  Codevelix  |  codevelix.com  |  info@codevelix.com  |  +92 306 4228502